## Risk Register
RISK REGISTER
ID | Risk Name | Date Raised | Risk & Impact Description | Likelihood | Consequences | Overall | Proposed Mitigation | Owner | Target Date to Resolve | Status
1 | Internet Connection Lost | 2021-09-23 | Cease of Internet functionality, due to a variety of reasons, that could entirely impede the access of online resources and fucntions | Unlikely | Minor | Low | Switch to offline software alternatives to continue the project and attempt to return the internet. | Max |  | open
2 | Github Failure | 2021-09-23 | Github fails to backup the data I held within it for some reason | Rare | Major | Moderate | Use the most recently saved renditions of the files and data stored locally on the computer. | Max |  | open
3 | Computer Crash | 2021-10-23 | The computer crashes and does not save any data or work I had made. | Unlikely | Moderate | Moderate | Restart computer and attempt to recover any work that was possibly auto-saved. | Max |  | open

## Issues Register
ISSUES REGISTER
ID | Date Raised | Project | Issue Title | Issue Description | Specific Deliverable/Milestone affected | Likelihood | Consequences | Overall Issue Rating | Proposed Resolution / Mitigating Action | Issue Owner | Target Date to Resolve | Progress Status / Commentary | Open / Closed

## Risk Matrix
Unitec RISK FRAMEWORK
Likelihood/Impact | Insignificant | Minor | Moderate | Major | Catastrophic
Almost Certain | Moderate | High | High | Extreme | Extreme
Likely | Moderate | Moderate | High | Extreme | Extreme
Possible | Low | Moderate | High | High | Extreme
Unlikely | Low | Low | Moderate | High | High
Rare | Low | Low | Moderate | Moderate | High

## Data (hidden)
Likelihood | Consequences
Almost Certain | Insignificant
Likely | Minor
Possible | Moderate
Unlikely | Major
Rare | Catastrophic